## WEEKLY PULL-OUT SCHEDULE
ℹ️ DEMO FILE — All data is fictitious for portfolio purposes only
WEEKLY PULL-OUT SCHEDULE & TESTING STATUS — Demo Data
Client | Stability No. | Product Name | Timepoint | Storage Conditions | Scheduled Retrieval | Window Start | Window End | Actual Pull Date | Testing Deadline | Days to Window | STATUS | Testing Status | Status Final | QIDR # | OOS | Comment | Documentation Completed | KEY (Stability+Timepoint) | Status Final (Clean) | Year | OOS (Clean) | Week (Actual Pull)
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | M9 | 30°C/65%RH | 2025-04-17 | 2025-04-10 | 2025-04-24 | 2025-04-17 | 2025-05-17 | 168:00 | Active | In Progress | Completed |  | N/A |  | Yes | 801¦M9 | Completed | 2025 | No OOS | Week 3 of April
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | M3 | 40°C/75%RH | [10 empty] | 26-03-007 |  |  | 801¦M3 | Pending |  | Open
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | M24 | 30°C/65%RH | [10 empty] | 26-03-007 |  |  | 801¦M24 | Pending |  | Open
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | M1 | 40°C/75%RH | 2025-05-22 | 2025-05-16 | 2025-05-30 | 2025-05-23 | 2025-06-22 | 168:00 | Active | In Progress |  |  | N/A |  |  | 801¦M1 | Pending | 2025 | No OOS | Week 4 of May
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | M12 | 5°C±3°C | 2026-05-19 | 2026-05-12 | 2026-05-26 | 2026-05-19 | 2026-06-18 | 168:00 | Active | In Progress |  |  | N/A |  |  | 801¦M12 | Pending | 2026 | No OOS | Week 3 of May
NovaMed Pharma | 821 | Zinc Lozenges 10mg | M9 | 5°C±3°C | 2025-04-28 | 2025-05-04 | 2025-05-18 | 2025-05-11 | 2025-06-10 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 821¦M9 | Not Completed | 2025 | No OOS | Week 2 of May
NovaMed Pharma | 821 | Zinc Lozenges 10mg | M18 | 40°C/75%RH | 2025-10-02 | 2025-09-27 | 2025-10-11 | 2025-10-04 | 2025-11-03 | 168:00 | Active | In Progress |  |  | 26-02-003 |  |  | 821¦M18 | Pending | 2025 | Open | Week 1 of October
NovaMed Pharma | 821 | Zinc Lozenges 10mg | M1 | 30°C/65%RH | 2025-04-28 | 2025-04-30 | 2025-05-14 | 2025-05-07 | 2025-06-06 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 821¦M1 | Not Completed | 2025 | No OOS | Week 1 of May
NovaMed Pharma | 821 | Zinc Lozenges 10mg | M24 | 40°C/75%RH | 2026-02-11 | 2026-02-15 | 2026-03-01 | 2026-02-22 | 2026-03-24 | 168:00 | Active | In Progress |  |  | N/A |  |  | 821¦M24 | Pending | 2026 | No OOS | Week 4 of February
NovaMed Pharma | 821 | Zinc Lozenges 10mg | M3 | 25°C/60%RH | 2025-07-14 | 2025-07-20 | 2025-08-03 | 2025-07-27 | 2025-08-26 | 168:00 | Active | In Progress | Completed |  | 26-02-003 |  | Yes | 821¦M3 | Completed | 2025 | Open | Week 4 of July
NovaMed Pharma | 832 | Turmeric Extract Capsules | M36 | 40°C/75%RH | [10 empty] | N/A |  |  | 832¦M36 | Pending |  | No OOS
NovaMed Pharma | 832 | Turmeric Extract Capsules | M9 | 30°C/65%RH | 2026-01-18 | 2026-01-17 | 2026-01-31 | 2026-01-24 | 2026-02-23 | 168:00 | Active | In Progress |  |  | N/A |  |  | 832¦M9 | Pending | 2026 | No OOS | Week 4 of January
NovaMed Pharma | 832 | Turmeric Extract Capsules | M18 | 30°C/65%RH | [10 empty] | N/A |  | Yes | 832¦M18 | Pending |  | No OOS
NovaMed Pharma | 832 | Turmeric Extract Capsules | M24 | 5°C±3°C | 2025-10-25 | 2025-10-27 | 2025-11-10 | 2025-11-03 | 2025-12-03 | 168:00 | Active | In Progress | Completed |  | 26-03-007 |  | Yes | 832¦M24 | Completed | 2025 | Open | Week 1 of November
NovaMed Pharma | 833 | CoQ10 100mg Softgels | M12 | 40°C/75%RH | 2025-08-23 | 2025-08-22 | 2025-09-05 | 2025-08-29 | 2025-09-28 | 168:00 | Active | In Progress | Not Completed | QIDR-880 | 26-04-012 |  |  | 833¦M12 | Not Completed | 2025 | Open | Week 5 of August
NovaMed Pharma | 833 | CoQ10 100mg Softgels | M24 | 30°C/65%RH | 2025-05-12 | 2025-05-18 | 2025-06-01 | 2025-05-25 | 2025-06-24 | 168:00 | Active | In Progress |  |  | N/A |  |  | 833¦M24 | Pending | 2025 | No OOS | Week 4 of May
NovaMed Pharma | 833 | CoQ10 100mg Softgels | M18 | 40°C/75%RH | 2026-04-20 | 2026-04-27 | 2026-05-11 | 2026-05-04 | 2026-06-03 | 168:00 | Active | In Progress |  |  | N/A |  |  | 833¦M18 | Pending | 2026 | No OOS | Week 1 of May
BioCore Labs | 843 | Iron Supplement Drops | M1 | 30°C/65%RH | [10 empty] | N/A |  |  | 843¦M1 | Pending |  | No OOS
BioCore Labs | 843 | Iron Supplement Drops | M3 | 30°C/65%RH | 2026-01-05 | 2025-12-31 | 2026-01-14 | 2026-01-07 | 2026-02-06 | 168:00 | Active | In Progress |  |  | 26-03-007 | OOS Closed |  | 843¦M3 | Pending | 2026 | Closed | Week 1 of January
BioCore Labs | 843 | Iron Supplement Drops | M12 | 5°C±3°C | 2026-02-28 | 2026-03-03 | 2026-03-17 | 2026-03-10 | 2026-04-09 | 168:00 | Active | In Progress |  |  | 26-04-012 | OOS Closed |  | 843¦M12 | Pending | 2026 | Closed | Week 2 of March
BioCore Labs | 843 | Iron Supplement Drops | M36 | 30°C/65%RH | 2025-09-21 | 2025-09-14 | 2025-09-28 | 2025-09-21 | 2025-10-21 | 168:00 | Active | In Progress |  |  | N/A |  |  | 843¦M36 | Pending | 2025 | No OOS | Week 3 of September
BioCore Labs | 851 | Vitamin C 500mg Tablets | M1 | 30°C/65%RH | [10 empty] | 26-01-001 | OOS Closed |  | 851¦M1 | Pending |  | Closed
BioCore Labs | 851 | Vitamin C 500mg Tablets | M24 | 5°C±3°C | 2026-06-17 | 2026-06-19 | 2026-07-03 | 2026-06-26 | 2026-07-26 | 168:00 | Active | In Progress |  |  | 26-04-012 |  |  | 851¦M24 | Pending | 2026 | Open | Week 4 of June
BioCore Labs | 851 | Vitamin C 500mg Tablets | M6 | 5°C±3°C | 2025-05-10 | 2025-05-13 | 2025-05-27 | 2025-05-20 | 2025-06-19 | 168:00 | Active | In Progress |  | QIDR-155 | 26-02-003 |  |  | 851¦M6 | Pending | 2025 | Open | Week 3 of May
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M18 | 25°C/60%RH | 2025-06-05 | 2025-06-04 | 2025-06-18 | 2025-06-11 | 2025-07-11 | 168:00 | Active | In Progress | Not Completed |  | 26-01-001 |  |  | 853¦M18 | Not Completed | 2025 | Open | Week 2 of June
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M24 | 25°C/60%RH | 2026-01-06 | 2025-12-31 | 2026-01-14 | 2026-01-07 | 2026-02-06 | 168:00 | Active | In Progress | Completed | QIDR-969 | N/A |  | Yes | 853¦M24 | Completed | 2026 | No OOS | Week 1 of January
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M1 | 5°C±3°C | 2025-10-19 | 2025-10-19 | 2025-11-02 | 2025-10-26 | 2025-11-25 | 168:00 | Active | In Progress |  | QIDR-268 | N/A |  |  | 853¦M1 | Pending | 2025 | No OOS | Week 4 of October
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M3 | 5°C±3°C | 2025-10-13 | 2025-10-10 | 2025-10-24 | 2025-10-17 | 2025-11-16 | 168:00 | Active | In Progress |  |  | 26-01-001 |  |  | 853¦M3 | Pending | 2025 | Open | Week 3 of October
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M12 | 40°C/75%RH | 2025-04-21 | 2025-04-23 | 2025-05-07 | 2025-04-30 | 2025-05-30 | 168:00 | Active | In Progress |  |  | N/A |  |  | 853¦M12 | Pending | 2025 | No OOS | Week 5 of April
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | M36 | 25°C/60%RH | 2025-11-30 | 2025-12-07 | 2025-12-21 | 2025-12-14 | 2026-01-13 | 168:00 | Active | In Progress |  | QIDR-182 | N/A |  |  | 853¦M36 | Pending | 2025 | No OOS | Week 2 of December
HealthSync Ltd | 856 | Probiotic Complex | M9 | 25°C/60%RH | 2026-01-14 | 2026-01-10 | 2026-01-24 | 2026-01-17 | 2026-02-16 | 168:00 | Active | In Progress |  |  | N/A |  |  | 856¦M9 | Pending | 2026 | No OOS | Week 3 of January
HealthSync Ltd | 856 | Probiotic Complex | M36 | 40°C/75%RH | 2025-12-19 | 2025-12-17 | 2025-12-31 | 2025-12-24 | 2026-01-23 | 168:00 | Active | In Progress |  |  | N/A |  |  | 856¦M36 | Pending | 2025 | No OOS | Week 4 of December
HealthSync Ltd | 856 | Probiotic Complex | M1 | 25°C/60%RH | 2026-02-28 | 2026-03-03 | 2026-03-17 | 2026-03-10 | 2026-04-09 | 168:00 | Active | In Progress |  |  | 26-04-012 |  |  | 856¦M1 | Pending | 2026 | Open | Week 2 of March
HealthSync Ltd | 875 | Turmeric Extract Capsules | M3 | 30°C/65%RH | 2025-05-24 | 2025-05-31 | 2025-06-14 | 2025-06-07 | 2025-07-07 | 168:00 | Active | In Progress |  |  | N/A |  |  | 875¦M3 | Pending | 2025 | No OOS | Week 1 of June
HealthSync Ltd | 875 | Turmeric Extract Capsules | M12 | 40°C/75%RH | 2026-05-24 | 2026-05-25 | 2026-06-08 | 2026-06-01 | 2026-07-01 | 168:00 | Active | In Progress |  | QIDR-206 | N/A |  |  | 875¦M12 | Pending | 2026 | No OOS | Week 1 of June
HealthSync Ltd | 875 | Turmeric Extract Capsules | M36 | 30°C/65%RH | 2025-06-04 | 2025-06-01 | 2025-06-15 | 2025-06-08 | 2025-07-08 | 168:00 | Active | In Progress | Completed |  | N/A |  | Yes | 875¦M36 | Completed | 2025 | No OOS | Week 2 of June
HealthSync Ltd | 882 | Turmeric Extract Capsules | M9 | 25°C/60%RH | 2026-06-08 | 2026-06-01 | 2026-06-15 | 2026-06-08 | 2026-07-08 | 168:00 | Active | In Progress | Completed |  | 26-03-007 | OOS Closed | Yes | 882¦M9 | Completed | 2026 | Closed | Week 2 of June
HealthSync Ltd | 882 | Turmeric Extract Capsules | M18 | 5°C±3°C | 2026-02-17 | 2026-02-14 | 2026-02-28 | 2026-02-21 | 2026-03-23 | 168:00 | Active | In Progress | Not Completed |  | 26-04-012 | OOS Closed |  | 882¦M18 | Not Completed | 2026 | Closed | Week 3 of February
HealthSync Ltd | 882 | Turmeric Extract Capsules | M24 | 40°C/75%RH | [10 empty] | N/A |  |  | 882¦M24 | Pending |  | No OOS
HealthSync Ltd | 882 | Turmeric Extract Capsules | M6 | 40°C/75%RH | [10 empty] | N/A |  |  | 882¦M6 | Pending |  | No OOS
HealthSync Ltd | 882 | Turmeric Extract Capsules | M36 | 30°C/65%RH | 2026-06-15 | 2026-06-08 | 2026-06-22 | 2026-06-15 | 2026-07-15 | 168:00 | Active | In Progress |  |  | N/A |  |  | 882¦M36 | Pending | 2026 | No OOS | Week 3 of June
PurePath Wellness | 896 | CoQ10 100mg Softgels | M9 | 30°C/65%RH | 2025-04-11 | 2025-04-06 | 2025-04-20 | 2025-04-13 | 2025-05-13 | 168:00 | Active | In Progress |  |  | 26-03-007 | OOS Closed |  | 896¦M9 | Pending | 2025 | Closed | Week 2 of April
PurePath Wellness | 896 | CoQ10 100mg Softgels | M24 | 5°C±3°C | 2025-05-20 | 2025-05-19 | 2025-06-02 | 2025-05-26 | 2025-06-25 | 168:00 | Active | In Progress | Completed |  | 26-04-012 |  | Yes | 896¦M24 | Completed | 2025 | Open | Week 4 of May
PurePath Wellness | 896 | CoQ10 100mg Softgels | M3 | 30°C/65%RH | 2026-06-18 | 2026-06-14 | 2026-06-28 | 2026-06-21 | 2026-07-21 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 896¦M3 | Not Completed | 2026 | No OOS | Week 3 of June
PurePath Wellness | 896 | CoQ10 100mg Softgels | M18 | 5°C±3°C | 2025-04-24 | 2025-04-29 | 2025-05-13 | 2025-05-06 | 2025-06-05 | 168:00 | Active | In Progress |  |  | 26-02-003 | OOS Closed |  | 896¦M18 | Pending | 2025 | Closed | Week 1 of May
PurePath Wellness | 907 | CoQ10 100mg Softgels | M3 | 40°C/75%RH | 2025-08-14 | 2025-08-07 | 2025-08-21 | 2025-08-14 | 2025-09-13 | 168:00 | Active | In Progress | Completed |  | 26-03-007 |  | Yes | 907¦M3 | Completed | 2025 | Open | Week 2 of August
PurePath Wellness | 907 | CoQ10 100mg Softgels | M6 | 40°C/75%RH | 2025-05-24 | 2025-05-23 | 2025-06-06 | 2025-05-30 | 2025-06-29 | 168:00 | Active | In Progress |  |  | N/A |  |  | 907¦M6 | Pending | 2025 | No OOS | Week 5 of May
PurePath Wellness | 907 | CoQ10 100mg Softgels | M36 | 40°C/75%RH | 2025-12-09 | 2025-12-16 | 2025-12-30 | 2025-12-23 | 2026-01-22 | 168:00 | Active | In Progress |  |  | N/A |  |  | 907¦M36 | Pending | 2025 | No OOS | Week 4 of December
PurePath Wellness | 927 | Iron Supplement Drops | M3 | 30°C/65%RH | 2025-09-09 | 2025-09-08 | 2025-09-22 | 2025-09-15 | 2025-10-15 | 168:00 | Active | In Progress |  |  | N/A |  |  | 927¦M3 | Pending | 2025 | No OOS | Week 3 of September
PurePath Wellness | 927 | Iron Supplement Drops | M18 | 25°C/60%RH | 2026-03-02 | 2026-03-06 | 2026-03-20 | 2026-03-13 | 2026-04-12 | 168:00 | Active | In Progress | Not Completed |  | 26-01-001 |  |  | 927¦M18 | Not Completed | 2026 | Open | Week 2 of March
PurePath Wellness | 927 | Iron Supplement Drops | M6 | 5°C±3°C | 2026-04-29 | 2026-05-01 | 2026-05-15 | 2026-05-08 | 2026-06-07 | 168:00 | Active | In Progress |  |  | 26-02-003 |  |  | 927¦M6 | Pending | 2026 | Open | Week 2 of May
PurePath Wellness | 927 | Iron Supplement Drops | M12 | 40°C/75%RH | 2026-04-28 | 2026-05-05 | 2026-05-19 | 2026-05-12 | 2026-06-11 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 927¦M12 | Not Completed | 2026 | No OOS | Week 2 of May
PurePath Wellness | 927 | Iron Supplement Drops | M24 | 30°C/65%RH | 2025-09-18 | 2025-09-12 | 2025-09-26 | 2025-09-19 | 2025-10-19 | 168:00 | Active | In Progress | Not Completed |  | 26-01-001 |  |  | 927¦M24 | Not Completed | 2025 | Open | Week 3 of September
VitaShield Inc | 943 | Magnesium Citrate Powder | M36 | 30°C/65%RH | 2026-03-23 | 2026-03-27 | 2026-04-10 | 2026-04-03 | 2026-05-03 | 168:00 | Active | In Progress |  |  | 26-04-012 |  |  | 943¦M36 | Pending | 2026 | Open | Week 1 of April
VitaShield Inc | 943 | Magnesium Citrate Powder | M9 | 5°C±3°C | [10 empty] | 26-03-007 |  | Yes | 943¦M9 | Pending |  | Open
VitaShield Inc | 943 | Magnesium Citrate Powder | M18 | 5°C±3°C | 2026-06-08 | 2026-06-02 | 2026-06-16 | 2026-06-09 | 2026-07-09 | 168:00 | Active | In Progress |  |  | N/A |  |  | 943¦M18 | Pending | 2026 | No OOS | Week 2 of June
VitaShield Inc | 963 | CoQ10 100mg Softgels | M36 | 30°C/65%RH | 2025-12-30 | 2025-12-30 | 2026-01-13 | 2026-01-06 | 2026-02-05 | 168:00 | Active | In Progress | Not Completed |  | 26-04-012 |  |  | 963¦M36 | Not Completed | 2026 | Open | Week 1 of January
VitaShield Inc | 963 | CoQ10 100mg Softgels | M12 | 40°C/75%RH | 2026-04-26 | 2026-04-27 | 2026-05-11 | 2026-05-04 | 2026-06-03 | 168:00 | Active | In Progress |  |  | N/A |  |  | 963¦M12 | Pending | 2026 | No OOS | Week 1 of May
VitaShield Inc | 963 | CoQ10 100mg Softgels | M18 | 25°C/60%RH | 2025-07-26 | 2025-07-23 | 2025-08-06 | 2025-07-30 | 2025-08-29 | 168:00 | Active | In Progress |  |  | 26-02-003 | OOS Closed |  | 963¦M18 | Pending | 2025 | Closed | Week 5 of July
VitaShield Inc | 963 | CoQ10 100mg Softgels | M24 | 5°C±3°C | 2026-03-20 | 2026-03-15 | 2026-03-29 | 2026-03-22 | 2026-04-21 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 963¦M24 | Not Completed | 2026 | No OOS | Week 4 of March
VitaShield Inc | 963 | CoQ10 100mg Softgels | M9 | 25°C/60%RH | 2025-10-30 | 2025-10-23 | 2025-11-06 | 2025-10-30 | 2025-11-29 | 168:00 | Active | In Progress | Not Completed | QIDR-883 | 26-03-007 |  |  | 963¦M9 | Not Completed | 2025 | Open | Week 5 of October
ClearDose Corp | 979 | Melatonin 3mg Tablets | M18 | 5°C±3°C | 2026-05-27 | 2026-05-26 | 2026-06-09 | 2026-06-02 | 2026-07-02 | 168:00 | Active | In Progress |  |  | N/A |  |  | 979¦M18 | Pending | 2026 | No OOS | Week 1 of June
ClearDose Corp | 979 | Melatonin 3mg Tablets | M6 | 5°C±3°C | 2025-04-09 | 2025-04-08 | 2025-04-22 | 2025-04-15 | 2025-05-15 | 168:00 | Active | In Progress |  | QIDR-737 | 26-03-007 | OOS Closed |  | 979¦M6 | Pending | 2025 | Closed | Week 3 of April
ClearDose Corp | 979 | Melatonin 3mg Tablets | M9 | 25°C/60%RH | 2025-10-10 | 2025-10-12 | 2025-10-26 | 2025-10-19 | 2025-11-18 | 168:00 | Active | In Progress |  |  | N/A |  |  | 979¦M9 | Pending | 2025 | No OOS | Week 3 of October
ClearDose Corp | 994 | Probiotic Complex | M1 | 5°C±3°C | 2025-09-10 | 2025-09-08 | 2025-09-22 | 2025-09-15 | 2025-10-15 | 168:00 | Active | In Progress |  |  | 26-01-001 | OOS Closed |  | 994¦M1 | Pending | 2025 | Closed | Week 3 of September
ClearDose Corp | 994 | Probiotic Complex | M6 | 40°C/75%RH | [10 empty] | N/A |  | Yes | 994¦M6 | Pending |  | No OOS
ClearDose Corp | 994 | Probiotic Complex | M9 | 30°C/65%RH | [10 empty] | N/A |  | Yes | 994¦M9 | Pending |  | No OOS
ClearDose Corp | 994 | Probiotic Complex | M24 | 30°C/65%RH | [10 empty] | N/A |  |  | 994¦M24 | Pending |  | No OOS
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | M36 | 40°C/75%RH | 2026-01-25 | 2026-01-29 | 2026-02-12 | 2026-02-05 | 2026-03-07 | 168:00 | Active | In Progress | Completed |  | N/A |  | Yes | 1013¦M36 | Completed | 2026 | No OOS | Week 1 of February
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | M18 | 30°C/65%RH | [10 empty] | 26-03-007 |  |  | 1013¦M18 | Pending |  | Open
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | M6 | 25°C/60%RH | 2026-02-13 | 2026-02-09 | 2026-02-23 | 2026-02-16 | 2026-03-18 | 168:00 | Active | In Progress | Completed |  | 26-01-001 | OOS Closed | Yes | 1013¦M6 | Completed | 2026 | Closed | Week 3 of February
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | M24 | 25°C/60%RH | 2025-04-17 | 2025-04-15 | 2025-04-29 | 2025-04-22 | 2025-05-22 | 168:00 | Active | In Progress |  |  | 26-03-007 | OOS Closed |  | 1013¦M24 | Pending | 2025 | Closed | Week 4 of April
ClearDose Corp | 1014 | Iron Supplement Drops | M36 | 5°C±3°C | 2025-06-19 | 2025-06-23 | 2025-07-07 | 2025-06-30 | 2025-07-30 | 168:00 | Active | In Progress |  |  | 26-01-001 | OOS Closed |  | 1014¦M36 | Pending | 2025 | Closed | Week 5 of June
ClearDose Corp | 1014 | Iron Supplement Drops | M1 | 25°C/60%RH | 2026-01-25 | 2026-01-22 | 2026-02-05 | 2026-01-29 | 2026-02-28 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1014¦M1 | Pending | 2026 | No OOS | Week 5 of January
ClearDose Corp | 1014 | Iron Supplement Drops | M9 | 5°C±3°C | 2026-04-13 | 2026-04-13 | 2026-04-27 | 2026-04-20 | 2026-05-20 | 168:00 | Active | In Progress |  | QIDR-286 | 26-03-007 |  |  | 1014¦M9 | Pending | 2026 | Open | Week 3 of April
ClearDose Corp | 1014 | Iron Supplement Drops | M6 | 40°C/75%RH | 2025-09-17 | 2025-09-22 | 2025-10-06 | 2025-09-29 | 2025-10-29 | 168:00 | Active | In Progress |  |  | 26-02-003 |  |  | 1014¦M6 | Pending | 2025 | Open | Week 5 of September
ClearDose Corp | 1014 | Iron Supplement Drops | M18 | 30°C/65%RH | 2025-07-06 | 2025-06-30 | 2025-07-14 | 2025-07-07 | 2025-08-06 | 168:00 | Active | In Progress | Not Completed |  | 26-03-007 |  |  | 1014¦M18 | Not Completed | 2025 | Open | Week 1 of July
ClearDose Corp | 1014 | Iron Supplement Drops | M12 | 40°C/75%RH | 2025-12-01 | 2025-12-01 | 2025-12-15 | 2025-12-08 | 2026-01-07 | 168:00 | Active | In Progress | Completed |  | N/A |  | Yes | 1014¦M12 | Completed | 2025 | No OOS | Week 2 of December
MediPro Australia | 1024 | Magnesium Citrate Powder | M36 | 40°C/75%RH | 2026-01-02 | 2025-12-31 | 2026-01-14 | 2026-01-07 | 2026-02-06 | 168:00 | Active | In Progress |  |  | 26-04-012 |  |  | 1024¦M36 | Pending | 2026 | Open | Week 1 of January
MediPro Australia | 1024 | Magnesium Citrate Powder | M12 | 30°C/65%RH | 2025-09-08 | 2025-09-02 | 2025-09-16 | 2025-09-09 | 2025-10-09 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1024¦M12 | Pending | 2025 | No OOS | Week 2 of September
MediPro Australia | 1024 | Magnesium Citrate Powder | M24 | 30°C/65%RH | 2026-03-28 | 2026-03-30 | 2026-04-13 | 2026-04-06 | 2026-05-06 | 168:00 | Active | In Progress |  |  | 26-01-001 | OOS Closed |  | 1024¦M24 | Pending | 2026 | Closed | Week 1 of April
MediPro Australia | 1024 | Magnesium Citrate Powder | M6 | 40°C/75%RH | 2025-09-02 | 2025-08-26 | 2025-09-09 | 2025-09-02 | 2025-10-02 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1024¦M6 | Pending | 2025 | No OOS | Week 1 of September
MediPro Australia | 1024 | Magnesium Citrate Powder | M9 | 5°C±3°C | [10 empty] | N/A |  |  | 1024¦M9 | Pending |  | No OOS
MediPro Australia | 1043 | Vitamin C 500mg Tablets | M36 | 25°C/60%RH | 2025-07-26 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 2025-09-07 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1043¦M36 | Pending | 2025 | No OOS | Week 2 of August
MediPro Australia | 1043 | Vitamin C 500mg Tablets | M9 | 30°C/65%RH | [10 empty] | N/A |  | Yes | 1043¦M9 | Pending |  | No OOS
MediPro Australia | 1043 | Vitamin C 500mg Tablets | M24 | 30°C/65%RH | 2025-05-11 | 2025-05-07 | 2025-05-21 | 2025-05-14 | 2025-06-13 | 168:00 | Active | In Progress | Completed |  | 26-03-007 | OOS Closed | Yes | 1043¦M24 | Completed | 2025 | Closed | Week 2 of May
MediPro Australia | 1043 | Vitamin C 500mg Tablets | M6 | 25°C/60%RH | 2025-11-09 | 2025-11-06 | 2025-11-20 | 2025-11-13 | 2025-12-13 | 168:00 | Active | In Progress |  |  | 26-03-007 |  |  | 1043¦M6 | Pending | 2025 | Open | Week 2 of November
MediPro Australia | 1043 | Vitamin C 500mg Tablets | M3 | 30°C/65%RH | 2026-04-23 | 2026-04-19 | 2026-05-03 | 2026-04-26 | 2026-05-26 | 168:00 | Active | In Progress | Not Completed |  | 26-01-001 | OOS Closed |  | 1043¦M3 | Not Completed | 2026 | Closed | Week 4 of April
MediPro Australia | 1046 | CoQ10 100mg Softgels | M1 | 5°C±3°C | 2025-04-14 | 2025-04-10 | 2025-04-24 | 2025-04-17 | 2025-05-17 | 168:00 | Active | In Progress |  |  | 26-01-001 | OOS Closed |  | 1046¦M1 | Pending | 2025 | Closed | Week 3 of April
MediPro Australia | 1046 | CoQ10 100mg Softgels | M9 | 5°C±3°C | 2025-08-02 | 2025-08-07 | 2025-08-21 | 2025-08-14 | 2025-09-13 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1046¦M9 | Pending | 2025 | No OOS | Week 2 of August
MediPro Australia | 1046 | CoQ10 100mg Softgels | M24 | 25°C/60%RH | 2025-06-02 | 2025-06-09 | 2025-06-23 | 2025-06-16 | 2025-07-16 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1046¦M24 | Pending | 2025 | No OOS | Week 3 of June
MediPro Australia | 1046 | CoQ10 100mg Softgels | M12 | 5°C±3°C | 2026-01-19 | 2026-01-23 | 2026-02-06 | 2026-01-30 | 2026-03-01 | 168:00 | Active | In Progress |  |  | 26-01-001 |  |  | 1046¦M12 | Pending | 2026 | Open | Week 5 of January
MediPro Australia | 1055 | Melatonin 3mg Tablets | M36 | 25°C/60%RH | 2025-08-07 | 2025-07-31 | 2025-08-14 | 2025-08-07 | 2025-09-06 | 168:00 | Active | In Progress | Completed | QIDR-788 | N/A |  | Yes | 1055¦M36 | Completed | 2025 | No OOS | Week 1 of August
MediPro Australia | 1055 | Melatonin 3mg Tablets | M1 | 5°C±3°C | 2026-01-21 | 2026-01-14 | 2026-01-28 | 2026-01-21 | 2026-02-20 | 168:00 | Active | In Progress | Not Completed | QIDR-285 | 26-04-012 | OOS Closed |  | 1055¦M1 | Not Completed | 2026 | Closed | Week 3 of January
MediPro Australia | 1055 | Melatonin 3mg Tablets | M12 | 5°C±3°C | 2025-10-31 | 2025-11-03 | 2025-11-17 | 2025-11-10 | 2025-12-10 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1055¦M12 | Pending | 2025 | No OOS | Week 2 of November
MediPro Australia | 1055 | Melatonin 3mg Tablets | M24 | 5°C±3°C | 2026-03-09 | 2026-03-03 | 2026-03-17 | 2026-03-10 | 2026-04-09 | 168:00 | Active | In Progress | Not Completed |  | 26-02-003 |  |  | 1055¦M24 | Not Completed | 2026 | Open | Week 2 of March
MediPro Australia | 1055 | Melatonin 3mg Tablets | M9 | 5°C±3°C | 2026-05-10 | 2026-05-15 | 2026-05-29 | 2026-05-22 | 2026-06-21 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1055¦M9 | Pending | 2026 | No OOS | Week 4 of May
MediPro Australia | 1055 | Melatonin 3mg Tablets | M6 | 5°C±3°C | 2025-05-18 | 2025-05-23 | 2025-06-06 | 2025-05-30 | 2025-06-29 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1055¦M6 | Pending | 2025 | No OOS | Week 5 of May
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M36 | 5°C±3°C | [10 empty] | 26-04-012 | OOS Closed |  | 1067¦M36 | Pending |  | Closed
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M24 | 40°C/75%RH | 2026-01-25 | 2026-01-30 | 2026-02-13 | 2026-02-06 | 2026-03-08 | 168:00 | Active | In Progress | Not Completed |  | N/A |  |  | 1067¦M24 | Not Completed | 2026 | No OOS | Week 1 of February
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M1 | 30°C/65%RH | 2025-05-15 | 2025-05-11 | 2025-05-25 | 2025-05-18 | 2025-06-17 | 168:00 | Active | In Progress | Completed |  | 26-04-012 | OOS Closed | Yes | 1067¦M1 | Completed | 2025 | Closed | Week 3 of May
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M3 | 5°C±3°C | 2025-12-06 | 2025-12-10 | 2025-12-24 | 2025-12-17 | 2026-01-16 | 168:00 | Active | In Progress |  |  | 26-03-007 | OOS Closed |  | 1067¦M3 | Pending | 2025 | Closed | Week 3 of December
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M6 | 25°C/60%RH | 2025-10-11 | 2025-10-07 | 2025-10-21 | 2025-10-14 | 2025-11-13 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1067¦M6 | Pending | 2025 | No OOS | Week 2 of October
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | M9 | 40°C/75%RH | 2025-10-25 | 2025-10-23 | 2025-11-06 | 2025-10-30 | 2025-11-29 | 168:00 | Active | In Progress |  |  | 26-01-001 | OOS Closed |  | 1067¦M9 | Pending | 2025 | Closed | Week 5 of October
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M6 | 30°C/65%RH | 2025-12-29 | 2025-12-28 | 2026-01-11 | 2026-01-04 | 2026-02-03 | 168:00 | Active | In Progress |  |  | 26-02-003 | OOS Closed |  | 1086¦M6 | Pending | 2026 | Closed | Week 1 of January
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M9 | 5°C±3°C | 2026-04-27 | 2026-04-26 | 2026-05-10 | 2026-05-03 | 2026-06-02 | 168:00 | Active | In Progress | Completed |  | 26-02-003 | OOS Closed | Yes | 1086¦M9 | Completed | 2026 | Closed | Week 1 of May
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M12 | 30°C/65%RH | 2026-05-16 | 2026-05-19 | 2026-06-02 | 2026-05-26 | 2026-06-25 | 168:00 | Active | In Progress | Not Completed |  | 26-04-012 | OOS Closed |  | 1086¦M12 | Not Completed | 2026 | Closed | Week 4 of May
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M24 | 5°C±3°C | 2026-06-19 | 2026-06-13 | 2026-06-27 | 2026-06-20 | 2026-07-20 | 168:00 | Active | In Progress |  |  | N/A |  |  | 1086¦M24 | Pending | 2026 | No OOS | Week 3 of June
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M36 | 5°C±3°C | [10 empty] | N/A |  |  | 1086¦M36 | Pending |  | No OOS
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | M3 | 40°C/75%RH | 2026-02-03 | 2026-02-07 | 2026-02-21 | 2026-02-14 | 2026-03-16 | 168:00 | Active | In Progress |  | QIDR-979 | N/A |  |  | 1086¦M3 | Pending | 2026 | No OOS | Week 2 of February

## INVOICE & REPORT TRACKER
ℹ️ DEMO FILE — All data is fictitious for portfolio purposes only
INVOICE & REPORT TRACKER — Demo Data
Client | Stability No. | Product Name | Batch No. | Timepoint | Invoice No. | Report Sent Deadline | Report Sent to Client Date | PO | Status Final | KEY (Stability+Timepoint) | Invoice Status
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | BN-9864 | M9 | IN2600004 | 2025-06-01 | 2025-05-18 | PO-90931 | Completed | 801¦M9 | Issued
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | BN-2480 | M24 | IN2600006 |  |  | PO-66881 | Pending | 801¦M24 | Issued
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | BN-8269 | M1 |  | 2025-07-07 |  |  | Pending | 801¦M1 | Pending
NovaMed Pharma | 801 | Omega-3 Fish Oil Capsules | BN-1753 | M12 |  | 2026-07-03 |  |  | Pending | 801¦M12 | Pending
NovaMed Pharma | 821 | Zinc Lozenges 10mg | BN-7141 | M9 |  | 2025-06-25 |  |  | Not Completed | 821¦M9 | Pending
NovaMed Pharma | 821 | Zinc Lozenges 10mg | BN-3950 | M18 |  | 2025-11-18 |  |  | Pending | 821¦M18 | Pending
NovaMed Pharma | 821 | Zinc Lozenges 10mg | BN-4945 | M1 |  | 2025-06-21 |  |  | Not Completed | 821¦M1 | Pending
NovaMed Pharma | 821 | Zinc Lozenges 10mg | BN-8555 | M24 |  | 2026-04-08 |  |  | Pending | 821¦M24 | Pending
NovaMed Pharma | 821 | Zinc Lozenges 10mg | BN-8622 | M3 |  | 2025-09-10 |  |  | Completed | 821¦M3 | Pending
NovaMed Pharma | 832 | Turmeric Extract Capsules | BN-2210 | M36 |  |  |  |  | Pending | 832¦M36 | Pending
NovaMed Pharma | 832 | Turmeric Extract Capsules | BN-5901 | M9 |  | 2026-03-10 |  |  | Pending | 832¦M9 | Pending
NovaMed Pharma | 832 | Turmeric Extract Capsules | BN-8484 | M18 |  |  |  |  | Pending | 832¦M18 | Pending
NovaMed Pharma | 832 | Turmeric Extract Capsules | BN-8916 | M24 |  | 2025-12-18 |  |  | Completed | 832¦M24 | Pending
NovaMed Pharma | 833 | CoQ10 100mg Softgels | BN-5847 | M12 |  | 2025-10-13 |  |  | Not Completed | 833¦M12 | Pending
NovaMed Pharma | 833 | CoQ10 100mg Softgels | BN-5497 | M24 |  | 2025-07-09 |  |  | Pending | 833¦M24 | Pending
BioCore Labs | 843 | Iron Supplement Drops | BN-9138 | M1 |  |  |  |  | Pending | 843¦M1 | Pending
BioCore Labs | 843 | Iron Supplement Drops | BN-6772 | M3 | IN2600046 | 2026-02-21 | 2026-02-13 | PO-93442 | Pending | 843¦M3 | Issued
BioCore Labs | 843 | Iron Supplement Drops | BN-2591 | M12 |  | 2026-04-24 |  |  | Pending | 843¦M12 | Pending
BioCore Labs | 843 | Iron Supplement Drops | BN-8222 | M36 |  | 2025-11-05 |  |  | Pending | 843¦M36 | Pending
BioCore Labs | 851 | Vitamin C 500mg Tablets | BN-6352 | M24 |  | 2026-08-10 |  |  | Pending | 851¦M24 | Pending
BioCore Labs | 851 | Vitamin C 500mg Tablets | BN-9837 | M6 |  | 2025-07-04 |  |  | Pending | 851¦M6 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-5465 | M18 |  | 2025-07-26 |  |  | Not Completed | 853¦M18 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-5835 | M24 |  | 2026-02-21 |  |  | Completed | 853¦M24 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-8673 | M1 |  | 2025-12-10 |  |  | Pending | 853¦M1 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-7511 | M3 |  | 2025-12-01 |  |  | Pending | 853¦M3 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-2479 | M12 |  | 2025-06-14 |  |  | Pending | 853¦M12 | Pending
HealthSync Ltd | 853 | Omega-3 Fish Oil Capsules | BN-3024 | M36 |  | 2026-01-28 |  |  | Pending | 853¦M36 | Pending
HealthSync Ltd | 856 | Probiotic Complex | BN-7242 | M9 |  | 2026-03-03 |  |  | Pending | 856¦M9 | Pending
HealthSync Ltd | 856 | Probiotic Complex | BN-4830 | M36 | IN2600080 | 2026-02-07 | 2026-02-07 | PO-13280 | Pending | 856¦M36 | Issued
HealthSync Ltd | 856 | Probiotic Complex | BN-4626 | M1 | IN2600083 | 2026-04-24 | 2026-04-29 | PO-18285 | Pending | 856¦M1 | Issued
HealthSync Ltd | 875 | Turmeric Extract Capsules | BN-7689 | M3 |  | 2025-07-22 |  |  | Pending | 875¦M3 | Pending
HealthSync Ltd | 875 | Turmeric Extract Capsules | BN-5986 | M12 |  | 2026-07-16 |  |  | Pending | 875¦M12 | Pending
HealthSync Ltd | 875 | Turmeric Extract Capsules | BN-9807 | M36 |  | 2025-07-23 |  |  | Completed | 875¦M36 | Pending
HealthSync Ltd | 882 | Turmeric Extract Capsules | BN-7866 | M9 |  | 2026-07-23 |  |  | Completed | 882¦M9 | Pending
HealthSync Ltd | 882 | Turmeric Extract Capsules | BN-2622 | M18 |  | 2026-04-07 |  |  | Not Completed | 882¦M18 | Pending
HealthSync Ltd | 882 | Turmeric Extract Capsules | BN-1536 | M24 |  |  |  |  | Pending | 882¦M24 | Pending
HealthSync Ltd | 882 | Turmeric Extract Capsules | BN-4868 | M6 |  |  |  |  | Pending | 882¦M6 | Pending
HealthSync Ltd | 882 | Turmeric Extract Capsules | BN-9920 | M36 |  | 2026-07-30 |  |  | Pending | 882¦M36 | Pending
PurePath Wellness | 896 | CoQ10 100mg Softgels | BN-7523 | M9 |  | 2025-05-28 |  |  | Pending | 896¦M9 | Pending
PurePath Wellness | 896 | CoQ10 100mg Softgels | BN-2501 | M24 | IN2600113 | 2025-07-10 | 2025-07-16 | PO-37801 | Completed | 896¦M24 | Issued
PurePath Wellness | 896 | CoQ10 100mg Softgels | BN-1828 | M3 |  | 2026-08-05 |  |  | Not Completed | 896¦M3 | Pending
PurePath Wellness | 896 | CoQ10 100mg Softgels | BN-4362 | M18 |  | 2025-06-20 |  |  | Pending | 896¦M18 | Pending
PurePath Wellness | 907 | CoQ10 100mg Softgels | BN-4817 | M6 |  | 2025-07-14 |  |  | Pending | 907¦M6 | Pending
PurePath Wellness | 907 | CoQ10 100mg Softgels | BN-1046 | M36 |  | 2026-02-06 |  |  | Pending | 907¦M36 | Pending
PurePath Wellness | 927 | Iron Supplement Drops | BN-9850 | M3 | IN2600125 | 2025-10-30 | 2025-10-23 | PO-32871 | Pending | 927¦M3 | Issued
PurePath Wellness | 927 | Iron Supplement Drops | BN-1243 | M18 |  | 2026-04-27 |  |  | Not Completed | 927¦M18 | Pending
PurePath Wellness | 927 | Iron Supplement Drops | BN-6304 | M6 |  | 2026-06-22 |  |  | Pending | 927¦M6 | Pending
PurePath Wellness | 927 | Iron Supplement Drops | BN-9619 | M24 |  | 2025-11-03 |  |  | Not Completed | 927¦M24 | Pending
VitaShield Inc | 943 | Magnesium Citrate Powder | BN-6931 | M36 |  | 2026-05-18 |  |  | Pending | 943¦M36 | Pending
VitaShield Inc | 943 | Magnesium Citrate Powder | BN-4629 | M9 |  |  |  |  | Pending | 943¦M9 | Pending
VitaShield Inc | 943 | Magnesium Citrate Powder | BN-5941 | M18 |  | 2026-07-24 |  |  | Pending | 943¦M18 | Pending
VitaShield Inc | 963 | CoQ10 100mg Softgels | BN-8847 | M36 | IN2600151 | 2026-02-20 | 2026-03-04 | PO-62640 | Not Completed | 963¦M36 | Issued
VitaShield Inc | 963 | CoQ10 100mg Softgels | BN-2204 | M12 |  | 2026-06-18 |  |  | Pending | 963¦M12 | Pending
VitaShield Inc | 963 | CoQ10 100mg Softgels | BN-2076 | M18 |  | 2025-09-13 |  |  | Pending | 963¦M18 | Pending
VitaShield Inc | 963 | CoQ10 100mg Softgels | BN-9984 | M24 |  | 2026-05-06 |  |  | Not Completed | 963¦M24 | Pending
VitaShield Inc | 963 | CoQ10 100mg Softgels | BN-9692 | M9 |  | 2025-12-14 |  |  | Not Completed | 963¦M9 | Pending
ClearDose Corp | 979 | Melatonin 3mg Tablets | BN-2624 | M18 |  | 2026-07-17 |  |  | Pending | 979¦M18 | Pending
ClearDose Corp | 979 | Melatonin 3mg Tablets | BN-4522 | M6 |  | 2025-05-30 |  |  | Pending | 979¦M6 | Pending
ClearDose Corp | 979 | Melatonin 3mg Tablets | BN-6553 | M9 | IN2600180 | 2025-12-03 | 2025-12-14 | PO-69441 | Pending | 979¦M9 | Issued
ClearDose Corp | 994 | Probiotic Complex | BN-7992 | M1 |  | 2025-10-30 |  |  | Pending | 994¦M1 | Pending
ClearDose Corp | 994 | Probiotic Complex | BN-8770 | M6 |  |  |  |  | Pending | 994¦M6 | Pending
ClearDose Corp | 994 | Probiotic Complex | BN-7105 | M24 |  |  |  |  | Pending | 994¦M24 | Pending
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | BN-6400 | M36 |  | 2026-03-22 |  |  | Completed | 1013¦M36 | Pending
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | BN-1842 | M18 |  |  |  |  | Pending | 1013¦M18 | Pending
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | BN-2697 | M6 |  | 2026-04-02 |  |  | Completed | 1013¦M6 | Pending
ClearDose Corp | 1013 | Omega-3 Fish Oil Capsules | BN-4674 | M24 |  | 2025-06-06 |  |  | Pending | 1013¦M24 | Pending
ClearDose Corp | 1014 | Iron Supplement Drops | BN-7022 | M36 |  | 2025-08-14 |  |  | Pending | 1014¦M36 | Pending
ClearDose Corp | 1014 | Iron Supplement Drops | BN-8030 | M1 |  | 2026-03-15 |  |  | Pending | 1014¦M1 | Pending
ClearDose Corp | 1014 | Iron Supplement Drops | BN-1430 | M9 | IN2600214 | 2026-06-04 | 2026-06-08 | PO-96223 | Pending | 1014¦M9 | Issued
ClearDose Corp | 1014 | Iron Supplement Drops | BN-5477 | M6 |  | 2025-11-13 |  |  | Pending | 1014¦M6 | Pending
ClearDose Corp | 1014 | Iron Supplement Drops | BN-6751 | M18 |  | 2025-08-21 |  |  | Not Completed | 1014¦M18 | Pending
MediPro Australia | 1024 | Magnesium Citrate Powder | BN-2140 | M36 |  | 2026-02-21 |  |  | Pending | 1024¦M36 | Pending
MediPro Australia | 1024 | Magnesium Citrate Powder | BN-2503 | M12 |  | 2025-10-24 |  |  | Pending | 1024¦M12 | Pending
MediPro Australia | 1024 | Magnesium Citrate Powder | BN-8432 | M24 |  | 2026-05-21 |  |  | Pending | 1024¦M24 | Pending
MediPro Australia | 1024 | Magnesium Citrate Powder | BN-2391 | M6 |  | 2025-10-17 |  |  | Pending | 1024¦M6 | Pending
MediPro Australia | 1024 | Magnesium Citrate Powder | BN-1815 | M9 |  |  |  |  | Pending | 1024¦M9 | Pending
MediPro Australia | 1043 | Vitamin C 500mg Tablets | BN-8957 | M36 |  | 2025-09-22 |  |  | Pending | 1043¦M36 | Pending
MediPro Australia | 1043 | Vitamin C 500mg Tablets | BN-9394 | M9 |  |  |  |  | Pending | 1043¦M9 | Pending
MediPro Australia | 1043 | Vitamin C 500mg Tablets | BN-8972 | M24 |  | 2025-06-28 |  |  | Completed | 1043¦M24 | Pending
MediPro Australia | 1043 | Vitamin C 500mg Tablets | BN-7475 | M6 |  | 2025-12-28 |  |  | Pending | 1043¦M6 | Pending
MediPro Australia | 1043 | Vitamin C 500mg Tablets | BN-5938 | M3 |  | 2026-06-10 |  |  | Not Completed | 1043¦M3 | Pending
MediPro Australia | 1046 | CoQ10 100mg Softgels | BN-5742 | M1 |  | 2025-06-01 |  |  | Pending | 1046¦M1 | Pending
MediPro Australia | 1046 | CoQ10 100mg Softgels | BN-3878 | M9 |  | 2025-09-28 |  |  | Pending | 1046¦M9 | Pending
MediPro Australia | 1046 | CoQ10 100mg Softgels | BN-9196 | M24 |  | 2025-07-31 |  |  | Pending | 1046¦M24 | Pending
MediPro Australia | 1046 | CoQ10 100mg Softgels | BN-2180 | M12 |  | 2026-03-16 |  |  | Pending | 1046¦M12 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-1307 | M36 |  | 2025-09-21 |  |  | Completed | 1055¦M36 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-8033 | M1 |  | 2026-03-07 |  |  | Not Completed | 1055¦M1 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-5743 | M12 |  | 2025-12-25 |  |  | Pending | 1055¦M12 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-3815 | M24 |  | 2026-04-24 |  |  | Not Completed | 1055¦M24 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-2443 | M9 |  | 2026-07-06 |  |  | Pending | 1055¦M9 | Pending
MediPro Australia | 1055 | Melatonin 3mg Tablets | BN-7560 | M6 |  | 2025-07-14 |  |  | Pending | 1055¦M6 | Pending
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-6562 | M36 |  |  |  |  | Pending | 1067¦M36 | Pending
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-9363 | M24 |  | 2026-03-23 |  |  | Not Completed | 1067¦M24 | Pending
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-6724 | M1 |  | 2025-07-02 |  |  | Completed | 1067¦M1 | Pending
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-4871 | M3 | IN2600290 | 2026-01-31 | 2026-01-19 | PO-29194 | Pending | 1067¦M3 | Issued
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-2234 | M6 |  | 2025-11-28 |  |  | Pending | 1067¦M6 | Pending
AlphaChem Pty Ltd | 1067 | CoQ10 100mg Softgels | BN-8601 | M9 |  | 2025-12-14 |  |  | Pending | 1067¦M9 | Pending
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | BN-6295 | M6 |  | 2026-02-18 |  |  | Pending | 1086¦M6 | Pending
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | BN-8205 | M9 |  | 2026-06-17 |  |  | Completed | 1086¦M9 | Pending
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | BN-1920 | M24 |  | 2026-08-04 |  |  | Pending | 1086¦M24 | Pending
AlphaChem Pty Ltd | 1086 | Turmeric Extract Capsules | BN-8404 | M36 |  |  |  |  | Pending | 1086¦M36 | Pending

## DASHBOARD
Year | (Todas)
Cuenta de Status Final | Etiquetas de columna
Etiquetas de fila | Completed | Not Completed | (en blanco) | Total general
AlphaChem Pty Ltd | 2 | 2 |  | 4
BioCore Labs
ClearDose Corp | 3 | 1 |  | 4
HealthSync Ltd | 3 | 2 |  | 5
MediPro Australia | 2 | 3 |  | 5
NovaMed Pharma | 3 | 3 |  | 6
PurePath Wellness | 2 | 4 |  | 6
VitaShield Inc |  | 3 |  | 3
Total general | 15 | 18 |  | 33
Year | (Todas)
Cuenta de OOS (Clean) | Etiquetas de columna
Etiquetas de fila | Closed | No OOS | Open | Total general
AlphaChem Pty Ltd | 7 | 5 |  | 12
BioCore Labs | 3 | 2 | 2 | 7
ClearDose Corp | 5 | 8 | 4 | 17
HealthSync Ltd | 2 | 12 | 3 | 17
MediPro Australia | 5 | 11 | 4 | 20
NovaMed Pharma |  | 11 | 6 | 17
PurePath Wellness | 2 | 5 | 5 | 12
VitaShield Inc | 1 | 3 | 4 | 8
Total general | 25 | 57 | 28 | 110
Cuenta de Invoice Status | Etiquetas de columna
Etiquetas de fila | Issued | Pending | Total general
AlphaChem Pty Ltd | 1 | 9 | 10
BioCore Labs | 1 | 5 | 6
ClearDose Corp | 2 | 13 | 15
HealthSync Ltd | 2 | 15 | 17
MediPro Australia |  | 20 | 20
NovaMed Pharma | 2 | 13 | 15
PurePath Wellness | 2 | 8 | 10
VitaShield Inc | 1 | 7 | 8
Total general | 11 | 90 | 101
Year | (Todas) |  |  |  | Week (Actual Pull) | (Todas)
Cuenta de OOS (Clean) | Etiquetas de columna |  |  |  | Cuenta de Status Final (Clean) | Etiquetas de columna
Etiquetas de fila | Closed | No OOS | Open | Total general | Etiquetas de fila | Completed | Not Completed | Pending | Total general
| 2 | 11 | 4 | 17 | AlphaChem Pty Ltd | 2 | 2 | 8 | 12
Week 3 of April | 2 | 1 | 1 | 4 | BioCore Labs |  |  | 7 | 7
Week 4 of May | 1 | 3 | 1 | 5 | ClearDose Corp | 3 | 1 | 13 | 17
Week 3 of May | 1 | 1 | 1 | 3 | HealthSync Ltd | 3 | 2 | 12 | 17
Week 2 of May | 1 | 2 | 1 | 4 | MediPro Australia | 2 | 3 | 15 | 20
Week 1 of October |  |  | 1 | 1 | NovaMed Pharma | 3 | 3 | 11 | 17
Week 1 of May | 2 | 3 |  | 5 | PurePath Wellness | 2 | 4 | 6 | 12
Week 4 of February |  | 1 |  | 1 | VitaShield Inc |  | 3 | 5 | 8
Week 4 of July |  |  | 1 | 1 | Total general | 15 | 18 | 77 | 110
Week 4 of January |  | 1 |  | 1
Week 1 of November |  |  | 1 | 1
Week 5 of August |  |  | 1 | 1
Week 1 of January | 2 | 1 | 2 | 5
Week 2 of March | 1 |  | 3 | 4
Week 3 of September | 1 | 2 | 1 | 4
Week 4 of June |  |  | 1 | 1
Week 2 of June | 1 | 2 | 1 | 4
Week 4 of October |  | 1 |  | 1
Week 3 of October |  | 1 | 1 | 2
Week 5 of April |  | 1 |  | 1
Week 2 of December |  | 2 |  | 2
Week 3 of January | 1 | 1 |  | 2
Week 4 of December |  | 2 |  | 2
Week 1 of June |  | 3 |  | 3
Week 3 of February | 2 |  |  | 2
Week 3 of June |  | 4 |  | 4
Week 2 of April | 1 |  |  | 1
Week 2 of August |  | 2 | 1 | 3
Week 5 of May |  | 2 |  | 2
Week 1 of April | 1 |  | 1 | 2
Week 5 of July | 1 |  |  | 1
Week 4 of March |  | 1 |  | 1
Week 5 of October | 1 |  | 1 | 2
Week 1 of February |  | 2 |  | 2
Week 4 of April | 2 |  |  | 2
Week 5 of June | 1 |  |  | 1
Week 5 of January |  | 1 | 1 | 2
Week 5 of September |  |  | 1 | 1
Week 1 of July |  |  | 1 | 1
Week 2 of September |  | 1 |  | 1
Week 1 of September |  | 1 |  | 1
Week 2 of November |  | 1 | 1 | 2
Week 1 of August |  | 1 |  | 1
Week 3 of December | 1 |  |  | 1
Week 2 of October |  | 1 |  | 1
Week 2 of February |  | 1 |  | 1
Total general | 25 | 57 | 28 | 110
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.